## Slide 1: Feature-Driven Development
Edel Sherratt, adapted from originals by Fred Long

## Slide 2: FDD and Project Management
Time is a valuable and scarce resource
Filling forms, answering email, dealing with ‘visits from the boss’ all consume time
Challenge: make information capture automatic and simple

## Slide 3: The Five Processes
Develop an Overall Model
Build a Features List
Plan by Features
Design by Features
Build by Features
object model and notes (more shape than content)
grouped list of features
development plan
design package (add more content to object model)
completed function
(From “Feature-Driven Development”, p.58.)

## Slide 4: Percentage completeness?
Fowler and Beck: asking a developer for a percentage of completeness generates a meaningless answer
A talented developer writes code without thinking too much …
  90% complete in a few days
  95% complete in a month
  99% complete in six months
  then leaves for a better job

## Slide 5: FDD doesn’t ask … it tells
FDD tells the feature teams what percentage complete they are
Each feature has six milestones
Chief programmers note when milestones are reached
This allows status of each feature to be tracked

## Slide 6: Progress Monitoring
Each feature has six milestones:
Design by Feature
Domain walkthrough
Design
Design inspection
1%
40%
3%
Build by Feature
Code
Code inspection
Promote to Build
45%
10%
1%
The percentage weightings should be as realistic as possible for the project

## Slide 7: FDD Wall Chart
A wall chart is produced listing every feature with the planned and actual date for each milestone
Features are colour-coded to indicate progress
  White: not started
  Yellow: in progress
  Green: completed
  Red: behind schedule
Stand back from the chart to view overall progress

## Slide 8: Overall Progress
Nov 2015
Manage Parts Inventory (13) 0%
Oct 2015
Ordering a New Car (16) 30%
Sep 2015
Arranging Financing (12) 78%
White
Not started
Yellow
In progress
Red
In trouble
Green
Complete
fwl
fwl
cwl
cwl
Oct 2015
Selling a Forecourt Car (7) 100%
(Adapted from Palmer & Felsing, p.86.)

## Slide 9: Accessibility
March 2016
Manage Parts Inventory (13) 0%
Jan 2016
Ordering a New Car (16) 30%
Sep 2015
Arranging Financing (12) 78%
White
Not started
Yellow
In progress
Red
In trouble
Green
Complete
fwl
fwl
cwl
cwl
Oct 2015
Selling a Forecourt Car (7) 100%
(Adapted from Palmer & Felsing, p.86.)
!


## Slide 10: Calculating Percentage Completeness
Only milestones that have been reached are counted
For example, a feature that has reached the coding stage would be 1 + 40 + 3 = 44% complete
… even if the coding is 90% complete
Percentage completion is calculated for each feature

## Slide 11: Results can be summarised in a table
Feature set | Number of features | Number not started | Number in progress | Number completed | Percentage completed
Schedule a service | 19 | 9 | 8 | 2 | 27.7%
Perform a service | 15 | 8 | 7 | 0 | 30.1%
Bill a service | 6 | 5 | 0 | 1 | 16.6%
Book a repair | 13 | 2 | 2 | 9 | 75.0%
Total | 53 | 24 | 17 | 12 | 38.7%
(From Palmer & Felsing p.82.)

## Slide 12: Who needs to know
Clients, sponsors, upper management …
soon learn to ask why a feature set is in trouble
Or why a feature set has been in progress for a long time and still isn’t ready
Or why Chief Programmer initials are changing frequently

## Slide 13: Summary – progress tracking in FDD
Certain information should be captured during a project:
  Design and development artifacts (what, how, why)
  Planning, scheduling and monitoring
  Who did what
As far as possible, this should be kept online and generated automatically
And it should be highly visible

## Slide 14: Key Differences from XP
FDD has an initial process when user requirements are gathered and formulated
FDD iterations involve small teams, rather than everyone
In FDD, code is owned by individual teams, not the whole group
FDD has a design stage and design reviews
Coding can become somewhat mechanical

## Slide 15: Key differences - continued
FDD involves a formal code review
FDD strongly discourages refactoring
FDD requires less intensive customer involvement than XP
FDD has defined progress tracking procedures
To use FDD’s progress tracking procedures effectively, project management tools are advisable
FDD works well with teams of mixed ability

## Slide 16: FDD, XP and software architecture
Software architecture can be planned or it can emerge as a result of refactoring
When is an emergent architecture likely to lead to a better software product, and when is a planned architecture likely to be better?

## Slide 17: Client availability
Sometimes, it is just not possible for the customer to be available on-site throughout the whole development period.
What hazards does this pose for the customer?
How can those hazards be reduced?

## Slide 18: Consider FDD if
Your project is large, but fairly well understood
Your client cannot be on-site throughout the project
Tracking progress is important
Your team is of mixed ability and experience

## Slide 19: Questions
?
?
?
?
?
?
?
?
?